## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Implement core functionality | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
2 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Implement GUI requirements | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
3 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Display Respond/Edit/Adjust Orders | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
4 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Develop Test Cases for Respond/Edit/Adjust Orders | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
5 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Test Approve Respond/Edit/Adjust Orders | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
6 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Crosscut: Field Validation-validating correct and valid info | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
7 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Crosscut: Data Dependency Validation- for field value combos | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
8 | 05. Orders | 5.02 | Respond/Edit/Adjust Orders | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
9 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Implement core functionality | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
10 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Implement GUI requirements | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
11 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Enable functionality Add/Delete Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
12 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Develop Test Cases for Add/Delete Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
13 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Test Approve Add/Delete Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
14 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Crosscut: Field Validation-validating correct and valid info | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
15 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Crosscut: Data Dependency Validation- for field value combos | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
16 | 06. Restaurant Inventory | 6.01 | Add/Delete Inventory Item | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
17 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Implement core functionality | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
18 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Implement GUI requirements | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
19 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Enable functionality for Adjust Inventory Item Cost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
20 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Develop Test Cases for Adjust Inventory Item Cost | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
21 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Test Approve Adjust Inventory Item Cost | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
22 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Crosscut: Field Validation-validating correct and valid info | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
23 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Crosscut: Data Dependency Validation- for field value combos | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
24 | 06. Restaurant Inventory | 6.02 | Adjust Inventory Item Cost | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
25 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Implement core functionality | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
26 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Implement GUI requirements | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
27 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Enable functionality Edit Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
28 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Develop Test Cases for Edit Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
29 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Test Approve Edit Inventory Item | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
30 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Crosscut: Field Validation-validating correct and valid info | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
31 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Crosscut: Data Dependency Validation- for field value combos | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
32 | 06. Restaurant Inventory | 6.03 | Edit Inventory Item | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
33 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Implement core functionality | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
34 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Implement GUI requirements | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
35 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Enable functionality Make Reservation | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
36 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Develop Test Cases for Make Reservation | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
37 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Test Approve Make Reservation | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
38 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Crosscut: Field Validation-validating correct and valid info | 2020-04-03 | 2020-04-24 | 100% | Janielle Vazquez
39 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Crosscut: Data Dependency Validation- for field value combos | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
40 | 07.Customer(Guest) Home | 7.01 | Make Reservation | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-03 | 2020-04-24 | 100% | Andy M / Ryan O'Hara
41 | 07.Customer(Guest) Home | 7.02 | Place order | Implement core functionality | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
42 | 07.Customer(Guest) Home | 7.02 | Place order | Implement GUI requirements | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
43 | 07.Customer(Guest) Home | 7.02 | Place order | Enable functionality Place order | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
44 | 07.Customer(Guest) Home | 7.02 | Place order | Develop Test Cases for Place order | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
45 | 07.Customer(Guest) Home | 7.02 | Place order | Test Approve Place order | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
46 | 07.Customer(Guest) Home | 7.02 | Place order | Crosscut: Field Validation-validating correct and valid info | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
47 | 07.Customer(Guest) Home | 7.02 | Place order | Crosscut: Data Dependency Validation- for field value combos | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
48 | 07.Customer(Guest) Home | 7.02 | Place order | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
49 | 08.Technical Support | 8.01 | Report a Bug | Implement core functionality | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
50 | 08.Technical Support | 8.01 | Report a Bug | Implement GUI requirements | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
51 | 08.Technical Support | 8.01 | Report a Bug | Enable functionality Report a Bug | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
52 | 08.Technical Support | 8.01 | Report a Bug | Develop Test Cases for Report a Bug | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
53 | 08.Technical Support | 8.01 | Report a Bug | Test Approve Report a Bug | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
54 | 08.Technical Support | 8.01 | Report a Bug | Crosscut: Field Validation-validating correct and valid info | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
55 | 08.Technical Support | 8.01 | Report a Bug | Crosscut: Data Dependency Validation- for field value combos | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
56 | 08.Technical Support | 8.01 | Report a Bug | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
57 | 08.Technical Support | 8.02 | Ask for Assistance | Implement core functionality | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
58 | 08.Technical Support | 8.02 | Ask for Assistance | Implement GUI requirements | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
59 | 08.Technical Support | 8.02 | Ask for Assistance | Enable functionality Ask for Assistance | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
60 | 08.Technical Support | 8.02 | Ask for Assistance | Develop Test Cases for Ask for Assistance | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
61 | 08.Technical Support | 8.02 | Ask for Assistance | Test Approve Ask for Assistance | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
62 | 08.Technical Support | 8.02 | Ask for Assistance | Crosscut: Field Validation-validating correct and valid info | 2020-04-25 | 2020-05-15 | 100% | Janielle Vazquez
63 | 08.Technical Support | 8.02 | Ask for Assistance | Crosscut: Data Dependency Validation- for field value combos | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara
64 | 08.Technical Support | 8.02 | Ask for Assistance | Crosscut: Connectivity- Ensures data stored if connection lost | 2020-04-25 | 2020-05-15 | 100% | Andy M / Ryan O'Hara