## Road Map l4
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/6/20 | Iteration 2 - 04/03/20 | Iteration 3 - 04/24/20 | Iteration 4 - 05/15/20
Module 1 - Registration | 01.01 Admin | 5
| 01.02 Guest | 5
| 01.02 Restaurant | 5 |  |  |  |  | features completed last semester
Module 2 - Login | 02.01 Admin Login | 3
| 02.02 Guest Login | 3
| 02.03 Restaurant Login | 3
Module 3 - Admin Home | 03.01 View Subscriptions | 4
| 03.02 Edit Subscription Prices/Features | 4
| 03.02 View inquiries | 4
Module 4 - Restaurant Home | 04.01 Add Menu Item | 4
| 04.02 Adjust pricing | 3
| 04.03 Edit Reservations | 3
| 04.04 Edit/Remove menu item | 3
| 04.05 Accept Payment | 5
Module 5 - Orders | 05.01 View Orders | 2
| 05.02 Respond/Edit/Adjust Orders | 3
Module 6 - Restaurant Inventory | 06.01 Add/Delete Inventory Item | 3
| 06.02 Adjust Inventory Item Cost | 3
| 06.03 Edit Inventory Item | 3
Module 7 - Customer (Guest)Home | 07.01 Make Reservation | 3
| 07.02 Place Order | 3 |  |  |  | x
Module 8 - Technical Support | 08.01 Report a bug | 5 |  |  |  | x
| 08.02 Ask for assistance | 5 |  |  |  | x
|  | Velocity : | 16 | 16 | 15 | 13

## Roles Traceability
User Roles vs. Features Matrix
User Roles | 01. Registration |  |  | 02. Login |  |  | 03. Admin Home |  |  | 04. Restaurnt Home |  |  |  |  | 05. Orders |  | 06. Restaurant Inventory |  |  | 07. Customer (Guest) |  | 08. Technical Support
| Admin | Guest | Restaurant | Admin Login | Guest Login | Restaurant Login | View Subscriptions | Edit Subscription Prices/Features | View inquiries | Add Menu Item | Adjust pricing | Edit Reservations | Edit/Remove menu item | Accept Payment | View Orders | Respond/Edit/Adjust Orders | Add/Delete Inventory Item | Adjust Inventory Item Cost | Edit Inventory Item | Make Reservation | Place Order | Report a Bug | Ask for assistance | Respond to assistance request
| 1.01 | 1.02 | 1.03 | 2.01 | 2.02 | 2.03 | 3.01 | 3.02 | 3.03 | 4.01 | 4.02 | 4.04 | 4.05 | 4.06 | 5.01 | 5.02 | 6.01 | 6.02 | 6.03 | 7.01 | 7.02 | 8.01 | 8.02 | 8.03
Guest |  | X |  |  | X | [9 empty] | X | X |  |  |  | X | X | X | X
Restaurant |  |  | X |  |  | X |  |  |  | X | X | X | X | X |  |  | X | X | X
Admin | X |  |  | X |  |  | X | X | X | [14 empty] | X

## Role Descriptions
USER ROLES
Customer (Guest)
Guest users are the general visitors that visit the site to look up menus and order food online.
Restaurant
These users are the technical users without admin privilege. They perform tasks like adding menu items, adjust pricing, edit reservations, edit/remove menu items, accept payment but cannot make changes in the original structure and core database.
Admin
These users are the core stakeholders who lay the foundation like the lead developer, product owner, lead business analyst, product manager and lead QA. They have all the privileges to edit, update or delete anything in the website or database.